## Overview
Aurora Platform Launch — Programme Overview
Portfolio roll-up. Figures pull live from each project sheet — edit a task there and this table updates.
# | Project | Owner | Status | Priority | Tasks | Est. Effort (d) | Actual Effort (d) | % Complete | End Date | Budget (d)
1 | Backend API | Sarah Klein | On Track | High | 6 | 40 | 20 | 53% | 2026-05-29 | 60
2 | Frontend App | Daniel Weber | At Risk | High | 6 | 48 | 21 | 40% | 2026-06-19 | 55
3 | Data Migration | Priya Nair | On Track | Medium | 5 | 29 | 7 | 23.45% | 2026-07-10 | 35
4 | QA & Release | Omar Haddad | Not Started | Medium | 5 | 34 | 0 | 0% | 2026-07-31 | 40
| PROGRAMME TOTAL |  |  |  | 22 | 151 | 48 | 31.26% |  | 190
| Programme completion |  | 31.26%
| Effort logged vs. estimated |  | 31.79%

## Backend API
Backend API — Aurora Platform Launch
Project Information
Project Owner | Sarah Klein
Status | On Track
Priority | High
Phase | Development
Start Date | 2026-01-12
End Date | 2026-05-29
Budget (days) | 60
Tasks
Task ID | Task Name | Description | Assignee | Est. Effort (d) | Actual Effort (d) | % Complete | Status | Comments
BE-01 | Auth service | OAuth2 + JWT session handling | Sarah Klein | 8 | 8 | 100% | Done | Reused module from prior project
BE-02 | User CRUD endpoints | REST endpoints for user objects | Marco Ruiz | 6 | 5 | 100% | Done
BE-03 | Rate limiting | Redis-backed throttling middleware | Marco Ruiz | 4 | 3 | 80% | In Progress | Tuning thresholds
BE-04 | Billing integration | Stripe webhooks + invoicing | Sarah Klein | 10 | 4 | 40% | In Progress | Blocked on vendor sandbox keys
BE-05 | Search API | Elastic-backed full-text search | Priya Nair | 9 | 0 | 0% | Not Started
BE-06 | API docs | OpenAPI spec + Swagger UI | Marco Ruiz | 3 | 0 | 0% | Not Started
TOTAL |  |  |  | 40 | 20 | 53%

## Frontend App
Frontend App — Aurora Platform Launch
Project Information
Project Owner | Daniel Weber
Status | At Risk
Priority | High
Phase | Development
Start Date | 2026-01-26
End Date | 2026-06-19
Budget (days) | 55
Tasks
Task ID | Task Name | Description | Assignee | Est. Effort (d) | Actual Effort (d) | % Complete | Status | Comments
FE-01 | Design system | Reusable component library + tokens | Lena Fischer | 10 | 11 | 100% | Done | Overran by 1 day
FE-02 | Onboarding flow | Signup, email verify, first-run wizard | Daniel Weber | 8 | 6 | 70% | In Progress
FE-03 | Dashboard | Charts + KPI widgets | Lena Fischer | 12 | 4 | 30% | In Progress | Waiting on BE-05 search API
FE-04 | Billing screens | Plan selection + payment UI | Daniel Weber | 7 | 0 | 0% | Not Started | Depends on BE-04
FE-05 | Accessibility pass | WCAG 2.1 AA audit + fixes | Lena Fischer | 6 | 0 | 0% | Not Started
FE-06 | Mobile responsive | Breakpoints + touch targets | Omar Haddad | 5 | 0 | 0% | Not Started
TOTAL |  |  |  | 48 | 21 | 40%

## Data Migration
Data Migration — Aurora Platform Launch
Project Information
Project Owner | Priya Nair
Status | On Track
Priority | Medium
Phase | Planning
Start Date | 2026-03-02
End Date | 2026-07-10
Budget (days) | 35
Tasks
Task ID | Task Name | Description | Assignee | Est. Effort (d) | Actual Effort (d) | % Complete | Status | Comments
DM-01 | Source audit | Catalogue legacy tables + owners | Priya Nair | 5 | 5 | 100% | Done
DM-02 | Mapping spec | Field-level mapping old->new schema | Priya Nair | 6 | 2 | 30% | In Progress
DM-03 | ETL pipeline | Extract/transform/load scripts | Marco Ruiz | 9 | 0 | 0% | Not Started
DM-04 | Dry-run migration | Full run against staging copy | Priya Nair | 5 | 0 | 0% | Not Started
DM-05 | Cutover plan | Runbook + rollback procedure | Priya Nair | 4 | 0 | 0% | Not Started
TOTAL |  |  |  | 29 | 7 | 23.45%

## QA & Release
QA & Release — Aurora Platform Launch
Project Information
Project Owner | Omar Haddad
Status | Not Started
Priority | Medium
Phase | Planning
Start Date | 2026-05-04
End Date | 2026-07-31
Budget (days) | 40
Tasks
Task ID | Task Name | Description | Assignee | Est. Effort (d) | Actual Effort (d) | % Complete | Status | Comments
QA-01 | Test plan | Scope, environments, exit criteria | Omar Haddad | 4 | 0 | 0% | Not Started
QA-02 | E2E test suite | Playwright automation of key flows | Omar Haddad | 12 | 0 | 0% | Not Started
QA-03 | Load testing | k6 scenarios + baseline report | Marco Ruiz | 6 | 0 | 0% | Not Started
QA-04 | Security review | Pen-test + dependency audit | Sarah Klein | 7 | 0 | 0% | Not Started
QA-05 | Release runbook | Deploy steps + go/no-go checklist | Omar Haddad | 5 | 0 | 0% | Not Started
TOTAL |  |  |  | 34 | 0 | 0%